## v3
Blackboard Group No 40 Class ZEE | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-11-18 | Saturday Nov.18 | PM class date plus |  |  | 13 | days | PM class date plus |  |  | 16 | days | PM class date plus |  |  | 19 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each Team member | Working with other members and understanding their thoughts. Assigning the task to get project done before time. | Share with team by uploading documentation to Bb 44 team channel's Files | Realistic planned hours: 3 hrs actual hours : 1.5 | Planned Date & Time of delivery: 23 Nov Actual Date: 23 Nov | DONE | Understanding the members of team by listening to their thoughts. Concising the thoughts to common goals and assigning solution accordingly. Bringing everyone on same note for completion of own module & early work submission. | Sharing the necessary documents on whatsapp group created, and inviting to work together by sending links of docs and sheet on group. | Realistic planned hours 2.5hrs | Planned date & time 22 Nov | DONE | Understanding the members of team by listening to their thoughts. Concising the thoughts to common goals and assigning solution accordingly. Bringing everyone on same note for completion of own module & early work submission. | Sharing the necessary documents on whatsapp group created, and inviting to work together by sending links of docs and sheet on group. |  | Planned date & time 22 Nov | DONE | Understanding the members of team by listening to their thoughts. Concising the thoughts to common goals and assigning solution accordingly. Bringing everyone on same note for completion of own module & early work submission. | Sharing the necessary documents on whatsapp group created, and inviting to work together by sending links of docs and sheet on group. |  | Planned date & time 22 Nov
Team Meeting Agenda ==> | Discussion on status of project, keeping eye on it, sharing files, requesting professor to review the work if needed | Delivering before time: all of our work should be done before and in time. We came on same page Project Plan excel file, Meetings of Minutes in .docx and zoom videos call for quieries and ideas sharing. | Realistic planned hours: 2hrs actual hours : 1.2hrs | Tuesday Nov.21 | DONE | Channeliziing the project plan, refining it, re-checking the module status assigned to each member, sharing files, asking professor to review the work if necessary. | All the work should be completed before the deadline and everyone is agreed on this: C code, Test cases, Meeting on word file, Excel file. | Realistic planned hours 3hrs+3hrs= 6hrs | Wednesday Nov.29 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.14 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.14 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.12 | TO DO
| request review from professor | Requesting the professor to review the project and asks him the feedback | N/A | Wednesday Nov.22 | DONE | request review from professor | Requesting the professor if help would be requiring on that note | TO BE DONE | Wednesday Nov.29 | TO DO | request review from professor | Requesting the professor if help would be requiring on that note | TO BE DONE | Saturday Dec.2 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." | TO BE DONE | Tuesday Dec.5 | TO DO
Jorge vivas Fundamentals | Declearing and schuduling the timelines, plaaning the meets, estimating time required for meetings. | Submission should be on the expected date and time. Should be going as per the meeting held and be working accordingly. | Realistic planned hours: 4hrs actual hours : 2hrs | Tuesday Nov.21 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and recodring the test cases for fundamental C code | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 5hrs | Thursday Nov.30 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and making log file on git fundamental C code | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 5hrs | Sunday Dec.3 | DONE | Completing all files related to fundamentals module along with git files. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. Adding it to git and pulling request | Realistic planned hours 2hrs | Wednesday Dec.6 | DONE |  |  |  | Tuesday Dec.13
Tien Vu To Manipulations | Keep the record for the group submission, organizing and managing the files. | Creating and helping to finalize the project plan is assigned. Also fulfilling the assistancy for the project plan, and documentation. Expecting to submit the work based on the deadlines assigned. | Realistic planned hours: 2.5hrs actual hours : 1.5hrs | Tuesday Nov.21 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and recodring the test cases for Manipulations C code. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 4hrs | Thursday Nov.30 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and making log file on git Manipulations C code. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 4hrs | Sunday Dec.3 | DONE | Completing all files related to manipulation module along with git files. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. Adding it to git and pulling request | Realistic planned hours 3hrs | Wednesday Dec.6 | DONE |  |  |  | Tuesday Dec.13
Arshia Keshavarzmotamedi Tokenizing | Adding the team member on the whatsapp group , taking charge wheather everyone is able to attend the meet as well pass on the useful information for project | Expecting to submit the work based on the deadlines provided, & came agreed to. Also fulfilled and assigned to work on Project plan and work on certain task assigned.. | Realistic planned hours: 5hrs actual hours : 3hrs | Tuesday Nov.21 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and recodring the test cases for Tokenizing C code. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 6hrs | Thursday Nov.30 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and making log file on git Tokenizing C code. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. | Realistic planned hours 6hrs | Sunday Dec.3 | DONE | Completing all files related to tokenizing module along with git files. | Completing, compiling and testing the code. Add the test results to test cases and sending it to Team leader for further processes. Adding it to git and pulling request | Realistic planned hours 2hrs | Wednesday Dec.6 | DONE |  |  |  | Tuesday Dec.13
Aditya Tambe Conversions Team Leader | Group Leader: Helping everyone in group, taking meetings and finalising the project. | Reviewing team work. Creating and finalizing the project plan, plan for meetings. assigned and adding the work of each team member | Realistic planned hours: 2hrs actual hours : 1hr | Wednesday Nov.22 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and recodring the test cases for Conversion C code. | Completing, compiling and testing the code. Add the test results to test cases and reviewing the other's work and assisting them if required based on work submitted and then finalizing the project V1. | Realistic planned hours 3hrs | Friday Dec.1 | DONE | Running the code, mentioned the comments wherever necessary, testing the code and making log file on gits for Conversion C code. Adding all the modules in the git repository. | Completing, compiling and testing the code. Add the test results to test cases and reviewing the other's work and assisting them if required based on work submitted and then finalizing the project V2. | Realistic planned hours 3hrs | Monday Dec.4 | DONE | Completing all files related to conversion module along with git files. | Completing, compiling and testing the code. Add the test results to test cases and check team work for further processes. Adding it to git and pulling request | Realistic planned hours 1.5hrs | Thursday Dec.7 | DONE |  |  |  | Wednesday Dec.14
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.